## 30-09-22
Status
1 | DC - 4 letter naming convention | AZUR for Azure
AWS for AWS
EMS - leave it as-is
LVDC-GCG --> LVDC
LVDC-ITAR --> LVDC
LVDC-Ranger--> LVDC
2 | AUDC | Categorize 1 cloud server to AZUR, P641TOMSQL01.WORDWAVE.COM.AU
3 | CADC | P060CTXSQLS01.CACUST.LOCAL\CITRIX, Check with Citrix team (Naveen Kumar Reddy) if this still exists in CADC instead of KADC | That old citrix environment has decommissioned already, not in use anymore. Only using for citrix purpose.
4 | EMS | Update instance names to all connected servers.
5 | SHDC | Add 6 servers manually one time | Sent SQL script to Tang, Tomas to reply with the details

## 18-10-22
| Items | Status | Comments
Phase 1 | 1. Copy and paste weekly contents into InventoryMaster.xlsx | Completed | This is part of my weekly mandatory task
| 2. Change notification failure operator emails to L1 team. | Completed | Failure notification email is set to L1 team
| 3. Domain name: To be added to all 'connectedserver names' or x to be used as the main key | Completed | Instance name column has a primary key and has FQDN on this column
| 4. Update the SQL edition to either Enterprise or Standard only (and not the lengthy name) | Completed | SQL edition column cut down to short name
| 5. Insert into archive to happen once a month | Completed | CMS _tracker_Archive - Created a job to load data (Occurs every first Monday of every 1 month(s))
Phase 2 | 1. Compare current and previous month's server count group by DC, domain. | Completed | Included servers group by DC in a new tab(excel) along with SQL inventory details to send email every week after data refresh, will update the same in sharepoint.
| 2. Add a trigger on inserts and deletes on the CMS_Tracker_Master and Archive tables. Email L1 team & Senthil. | Completed | Created trigger FOR insert, update and delete on CMS_Tracker_master and CMS_Tracker_master_Archive tables, except for EPIQCORP\svc_P054SQLMGMT3a account on which the master table updates
| 3. Denydata writer on all accounts except Inventorycollector on the above two tables. | Completed
| 4. Agent job to delete servers with DECOM status for over 6 months. | Ignored